ClinicalFlow AI

Complete Project Plan — Management Review

Document Version: 2.1  |  Prepared: 11 Sep 2026
Project Start: 10 Sep 2026  |  Planned End: 01 Oct 2026
Stack: FastAPI · SQLAlchemy · React 19 · Gemini · Deepgram

Purpose: This document presents the full chronological delivery plan for ClinicalFlow AI — modules, sub-modules, features, status, AI agent allocation, and a future Admin module — for management visibility and tracking.

# 1. Executive Summary

ClinicalFlow AI is a full-stack clinical workflow platform that mirrors a real hospital journey: walk-in registration (Receptionist) → doctor consultation (Doctor) → clinical orders & sign-off, augmented by three AI agents for triage, medical scribing, and clinical decision support.

Current overall status: Phase 0 & Phase 1 complete (backend). Phase 2 (Scribe) in progress.

Roles live today: Receptionist, Doctor. Future role: Admin (manage doctors & master data).

# 2. User Roles (RBAC)

| Role | Primary Responsibilities | Status |
| --- | --- | --- |
| Receptionist | Register patients, chief complaint, trigger triage, payment, waiting queue | Backend Done |
| Doctor | View queue, pre-visit brief, record consult, SOAP review, CDS review, finalize | In Progress |
| Admin (Future) | Add/edit doctors & specialties, manage users, clinic master data, configuration | Planned (Phase 7) |

# 3. AI Agents — Features & Module Allocation

Agents are allotted chronologically to the patient journey modules. Each agent belongs to a specific phase and must not be started out of order relative to the clinical workflow.

## 3.1 Agent Summary

## 3.2 Agent 1 — Smart Triage (Module: Receptionist Triage)

File: backend/app/services/agents/triage_agent.py

Triggered by: POST /patients/{id}/checkin

Features: recommended specialty; acuity (Routine / Urgent / Emergency); risk level; pre-visit brief; confidence score

Doctor assignment: least-loaded available specialist matching specialty

Fallback: rules-based triage when Gemini API unavailable

Status: Complete (backend verified)

## 3.3 Agent 2 — Ambient Scribe (Module: Doctor Consultation)

File: backend/app/services/agents/scribe_agent.py

Triggered by: POST /consultations/{id}/scribe

Features: Deepgram Nova-2 transcription (Gemini fallback); SOAP Subjective / Objective / Assessment / Plan; key findings

UI: Consultation Room + browser audio recorder / upload

Status: In Progress

## 3.4 Agent 3 — CDS Orders (Module: Clinical Orders & Sign-off)

File: backend/app/services/agents/cds_orders_agent.py

Triggered by: POST /consultations/{id}/cds; finalized via POST /encounters/{id}/finalize

Features: lab/imaging suggestions; medications with dose/route; ICD-10 codes; referrals; drug-interaction warnings; follow-up

Doctor must approve/reject suggestions before sign-off (human-in-the-loop)

Status: Not Started

# 4. Chronological Master Plan (Modules → Sub-modules → Features → Status)

Modules are ordered by delivery sequence.

## 4.1 Sprint / Phase Timeline Overview

| Sprint | Dates | Phase / Module | Key Deliverables | Status |
| --- | --- | --- | --- | --- |
| Sprint 0 | 11/09/2026 | Phase 0 — Foundation | Config, JWT auth, models, seed users, RBAC prep | Complete ✅ |
| Sprint 1 | 11/09/2026 | Phase 1 — Intake & Triage | Patient API, Agent 1, triage UI plan | Backend Complete ✅ |
| Sprint 2 | 11/09/2026 | Phase 1 — Payment & Queue | Mock payment, queue APIs, receptionist dashboard | Backend Complete ✅ |
| Sprint 3 |  | Phase 2 — Consultation | Audio recorder, Agent 2 SOAP, consult room | In Progress 🔄 |
| Sprint 4 |  | Phase 3 — CDS & Sign-off | Agent 3, orders UI, encounter finalize | Not Started ⏳ |
| Sprint 5 |  | Phase 4 — Audit & Polish | Audit coverage, UX polish, error handling | Not Started ⏳ |
| Sprint 6 |  | Phase 5 — Testing & QA | Unit/component tests, E2E smoke checklist | Not Started ⏳ |
| Sprint 7 |  | Phase 6 — Deployment | Postgres, Docker, CI/CD, auth hardening | Not Started ⏳ |
| Sprint 8 |  | Phase 7 — Admin (Future) | Admin role, doctor CRUD, master data | Planned (Future) ⏳ |

## 4.2 Phase 0 — Foundation & Infrastructure

| Sub-module | Features | Owner Area | Status |
| --- | --- | --- | --- |
| Config cleanup | Single Settings class (Gemini, Deepgram, JWT) | Backend | Complete |
| User model & auth | Signup, login, /me; bcrypt + JWT | Backend | Complete |
| Seed users | Demo Receptionist & Doctor accounts | Backend | Complete |
| Schema additions | Patient queue fields; TriageResult, Encounter, Payment models | Backend | Complete |
| ID helpers | USR-, TRI-, ENC-, PAY-, PAT- generators | Backend | Complete |
| Role-based sidebar | Receptionist vs Doctor navigation | Frontend | Planned |
| Login / Signup pages | Auth guard, logout, session hydrate | Frontend | Planned |

## 4.3 Phase 1 — Receptionist Experience (Intake & Triage)

Status: Backend Complete ✅  |  Agent: Agent 1 (allotted)

| Sub-module | Features / APIs | Agent Link | Status |
| --- | --- | --- | --- |
| Patient registration | POST /patients — demographics, contact, insurance, history | — | Complete |
| Check-in & triage | POST /patients/{id}/checkin — chief complaint, vitals | Agent 1 | Complete |
| Smart Triage agent | Specialty, doctor routing, acuity, pre-visit brief | Agent 1 | Complete |
| Payment (mock) | POST /payments — Cash/Card/UPI/Insurance | — | Complete |
| Queue management | GET /queue, GET /queue/all | Uses Agent 1 assignment | Complete |
| New Patient UI | /receptionist/new-patient form | — | Planned |
| Triage Station UI | /receptionist/triage/:id result panel | Agent 1 | Planned |
| Checkout UI | /receptionist/checkout/:id receipt + queue confirm | — | Planned |
| Receptionist dashboard | KPIs, live waiting queue, + New Patient | — | Planned |

## 4.4 Phase 2 — Doctor Experience (Consultation & Scribing)

Status: In Progress 🔄  |  Agent: Agent 2 (allotted)

| Sub-module | Features / APIs | Agent Link | Status |
| --- | --- | --- | --- |
| Doctor queue dashboard | My Queue by position, acuity, Start Consultation | Uses Agent 1 brief | Planned |
| Consultation room | 3-panel UI: brief + recorder + SOAP | Agent 1 + Agent 2 | Planned |
| Audio recorder | Web Audio / MediaRecorder; upload .webm/.wav | Feeds Agent 2 | Planned |
| Upload / transcribe | Existing consultation upload & Deepgram path | Agent 2 Step A | Existing |
| Scribe agent + SOAP | POST /consultations/{id}/scribe — SOAP JSON | Agent 2 | In Progress |
| Encounter SOAP fields | Persist SOAP on Consultation / Encounter | Agent 2 | In Progress |

## 4.5 Phase 3 — Clinical Decision Support & Sign-off

Status: Not Started ⏳  |  Agent: Agent 3 (allotted)

| Sub-module | Features / APIs | Agent Link | Status |
| --- | --- | --- | --- |
| CDS Orders agent | Labs, meds, ICD-10, referrals, warnings | Agent 3 | Not Started |
| CDS API | POST /consultations/{id}/cds | Agent 3 | Not Started |
| Encounter finalize | POST /encounters/{id}/finalize — approved items + referrals | Uses Agent 3 output | Not Started |
| Clinical Orders UI | /doctor/review/:id checkboxes + Sign & Finalize | Agent 3 | Not Started |

## 4.6 Phase 4 — Audit, Compliance & Polish

Status: Not Started ⏳

| Sub-module | Features | Status |
| --- | --- | --- |
| Comprehensive audit logging | Register, triage, payment, queue, consult, scribe, CDS, finalize | Not Started |
| Frontend polish | Skeletons, toasts, transitions, mobile sidebar, acuity color coding | Not Started |
| Error / edge cases | No API key fallbacks, empty transcript, queue races, retries | Not Started |

## 4.7 Phase 5 — Testing & Quality Assurance

Status: Not Started ⏳

| Sub-module | Features | Status |
| --- | --- | --- |
| Backend unit tests | patients, triage, scribe, CDS, payments, encounters, audit (mocked AI) | Not Started |
| Frontend component tests | AudioRecorder, registration, triage, clinical orders | Not Started |
| E2E smoke checklist | Full receptionist → doctor → finalize manual path | Not Started |

## 4.8 Phase 6 — Deployment & Production Readiness

Status: Not Started ⏳

| Sub-module | Features | Status |
| --- | --- | --- |
| DB migration | SQLite → PostgreSQL via Alembic | Not Started |
| Auth hardening | httpOnly cookies, refresh tokens, rate limit, password strength | Not Started |
| Dockerization | Backend/frontend Dockerfiles + docker-compose | Not Started |
| CI/CD | GitHub Actions — pytest + frontend build | Not Started |

## 4.9 Phase 7 — Admin Module (Future Roadmap)

Status: Planned (Future)

After MVP (Receptionist + Doctor + 3 agents), introduce an Admin role so clinic managers can maintain doctors and operational master data without code or DB changes.

### Admin — Sub-modules & Features

| Sub-module | Features | Priority | Status |
| --- | --- | --- | --- |
| Admin authentication | Role = Admin; JWT; protect /admin/* routes | P0 | Future |
| Doctor management | Add / edit / deactivate doctors; specialty; availability; contact | P0 | Future |
| Specialty master | CRUD specialties used by Agent 1 routing | P0 | Future |
| User management | Create Receptionist/Doctor accounts; reset password; activate/deactivate | P0 | Future |
| Clinic / facility info | Clinic name, address, hours, default consultation fee | P1 | Future |
| Fee configuration | Configure consultation / follow-up / lab fee amounts for payment module | P1 | Future |
| Referral rules admin | Manage condition → specialist routing rules (supports triage fallback) | P1 | Future |
| Audit & reports view | Admin-wide audit trail; daily registrations / revenue summary | P2 | Future |
| System settings | Feature flags (AI on/off), API key status indicators (non-secret) | P2 | Future |

### Admin — Suggested APIs (Future)

POST /admin/doctors — create doctor (maps to specialists / users)

PUT /admin/doctors/{id} — update specialty, availability, load

GET /admin/doctors — list all doctors

POST /admin/users — create Receptionist/Doctor/Admin accounts

PUT /admin/settings/fees — consultation fee used by payment checkout

CRUD /admin/specialties and /admin/referral-rules

### Admin — UI Pages (Future)

/admin/dashboard — clinic KPIs

/admin/doctors — add/edit doctors (primary request from management)

/admin/users — staff accounts

/admin/specialties & /admin/rules — master data for Agent 1

/admin/settings — fees, facility info

# 5. End-to-End Workflow (Chronological Module Order)

Patient journey with agents mapped at the correct step:

1. [Admin Future] Maintain doctors & specialties — enables correct Agent 1 routing

2. Receptionist registers patient

3. Receptionist check-in + Agent 1 Triage —

4. Receptionist processes payment —

5. Patient enters doctor queue —

6. Doctor starts consult; reviews Agent 1 pre-visit brief —

7. Record/upload audio → Agent 2 Scribe (transcript + SOAP) — Phase 2 🔄

8. Agent 3 CDS suggestions (labs/meds/ICD/referrals) — Phase 3

9. Doctor reviews, approves, Sign & Finalize encounter — Phase 3

10. Audit trail for all actions — Phase 4

# 6. What Works Today (Verified Backend)

| Order | Capability | Endpoint / Note | Status |
| --- | --- | --- | --- |
| 1 | Auth login / me | POST /auth/login, GET /auth/me | Working |
| 2 | Register patient | POST /patients | Working |
| 3 | Check-in + Agent 1 | POST /patients/{id}/checkin | Working |
| 4 | Mock payment | POST /payments | Working |
| 5 | View queues | GET /queue, GET /queue/all | Working |
| 6 | Scribe (SOAP) | POST /consultations/{id}/scribe | In Progress |
| 7 | CDS + finalize | CDS / encounters endpoints | Not Started |

Demo accounts:

| Email | Password | Role |
| --- | --- | --- |
| ananya@clinicalflow.demo | receptionist123 | Receptionist |
| neha@clinicalflow.demo | doctor123 | Doctor |

# 7. Technology Stack

| Layer | Technology |
| --- | --- |
| Backend | FastAPI (Python 3.13), SQLAlchemy, SQLite → PostgreSQL |
| Frontend | Vite, React 19, TanStack Router, Tailwind CSS 4, Radix/shadcn |
| AI — Triage & CDS | Google Gemini API (gemini-2.5-flash) |
| AI — Transcription | Deepgram Nova-2 (Gemini fallback) |
| Auth | JWT (python-jose), passlib/bcrypt |
| Deploy (planned) | Docker, docker-compose, GitHub Actions CI |

# 8. Risk Register

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Gemini rate limits / quota | Agents fail | Rules-based fallback for every agent |
| Deepgram key invalid | No transcription | Gemini fallback transcription |
| SQLite locking under load | Write failures | Move to PostgreSQL in Phase 6 |
| Large audio uploads | Timeouts | Max file size + chunked upload later |
| SOAP quality vs audio quality | Unreliable notes | Disclaimer: AI-generated — doctor must review |
| Admin delayed | Manual doctor seed only | Keep seed specialists until Phase 7 |

# 9. Success Criteria for Management Sign-off

Receptionist can register → triage (Agent 1) → pay → queue without errors.

Doctor can open queue → consult → Agent 2 SOAP → Agent 3 CDS → finalize.

All critical actions appear in audit trail.

Agents degrade gracefully when AI keys are missing.

MVP deployable via Docker with PostgreSQL (Phase 6).

Future: Admin can add doctors/specialties without developer intervention (Phase 7).